## WBS
SAP Ariba SLP + Buying Implementation Plan - Acme Industrial
Task ID | Phase | Workstream | Task | Owner | Start | End | Duration (days) | % Complete | Status | Notes
P-01 | Prepare | PMO | Project kickoff meeting | Sara Lindqvist / Marcus Chen | 2026-06-15 | 2026-06-15 | 1 | 0% | Not Started
P-02 | Prepare | PMO | Governance model & steering committee setup | Sara Lindqvist | 2026-06-15 | 2026-06-19 | 5 | 0% | Not Started
P-03 | Prepare | PMO | Project charter sign-off | Sara Lindqvist | 2026-06-18 | 2026-06-22 | 5 | 0% | Not Started
P-04 | Prepare | PMO | Communication plan | Helena Ruiz | 2026-06-22 | 2026-06-26 | 5 | 0% | Not Started
P-05 | Prepare | Technical | Ariba realm provisioning (test + prod) | Ravi Subramanian | 2026-06-15 | 2026-06-22 | 8 | 0% | Not Started
P-06 | Prepare | Technical | SAP integration prerequisites checklist | Yusuf Khalil | 2026-06-22 | 2026-06-26 | 5 | 0% | Not Started
P-07 | Prepare | Change | Stakeholder map & change impact baseline | Olivia Park | 2026-06-15 | 2026-06-26 | 12 | 0% | Not Started
E-01 | Explore | SLP | Supplier data discovery & cleansing strategy | Anika Patel | 2026-06-29 | 2026-07-03 | 5 | 0% | Not Started
E-02 | Explore | SLP | Supplier registration form design workshop | Anika Patel | 2026-07-06 | 2026-07-10 | 5 | 0% | Not Started
E-03 | Explore | SLP | Supplier qualification questionnaire design | Anika Patel | 2026-07-07 | 2026-07-14 | 8 | 0% | Not Started
E-04 | Explore | SLP | Supplier segmentation & approval workflow design | Anika Patel | 2026-07-13 | 2026-07-17 | 5 | 0% | Not Started
E-05 | Explore | Buying | Procurement policy review & catalog strategy | James Whitaker | 2026-06-29 | 2026-07-03 | 5 | 0% | Not Started
E-06 | Explore | Buying | Guided Buying landing page & tile design | James Whitaker | 2026-07-06 | 2026-07-10 | 5 | 0% | Not Started
E-07 | Explore | Buying | Approval rules & spend authorization matrix design | James Whitaker | 2026-07-13 | 2026-07-17 | 5 | 0% | Not Started
E-08 | Explore | Buying | Catalog enablement plan (CIF, PunchOut, BMEcat) | James Whitaker | 2026-07-20 | 2026-07-24 | 5 | 0% | Not Started
E-09 | Explore | Technical | Integration design (SLP master data, PR/PO, GR, invoice) | Yusuf Khalil | 2026-06-29 | 2026-07-17 | 19 | 0% | Not Started
E-10 | Explore | Technical | SSO & user provisioning design | Tom Becker | 2026-07-14 | 2026-07-17 | 4 | 0% | Not Started
E-11 | Explore | Data | Vendor master cleansing & migration approach | Rina Takahashi | 2026-06-29 | 2026-07-24 | 26 | 0% | Not Started
E-12 | Explore | Change | Training needs analysis | Olivia Park | 2026-07-27 | 2026-07-31 | 5 | 0% | Not Started
R-01 | Realize | SLP | Configure registration & qualification forms | Anika Patel | 2026-08-03 | 2026-08-14 | 12 | 0% | Not Started
R-02 | Realize | SLP | Configure supplier segmentation & approval flows | Anika Patel | 2026-08-17 | 2026-08-21 | 5 | 0% | Not Started
R-03 | Realize | SLP | Configure supplier 360 view & modular questionnaires | Anika Patel | 2026-08-24 | 2026-08-28 | 5 | 0% | Not Started
R-04 | Realize | Buying | Configure Guided Buying tiles, forms, and policies | James Whitaker | 2026-08-03 | 2026-08-14 | 12 | 0% | Not Started
R-05 | Realize | Buying | Configure approval flows & substitute approvers | James Whitaker | 2026-08-17 | 2026-08-21 | 5 | 0% | Not Started
R-06 | Realize | Buying | Configure commodity codes & catalog views | James Whitaker | 2026-08-24 | 2026-08-28 | 5 | 0% | Not Started
R-07 | Realize | Buying | Onboard pilot catalogs (CIF + PunchOut) | James Whitaker | 2026-08-31 | 2026-09-04 | 5 | 0% | Not Started
R-08 | Realize | Technical | Build SAP <-> Ariba integration (CIG / API) | Yusuf Khalil | 2026-08-03 | 2026-09-11 | 40 | 0% | Not Started
R-09 | Realize | Technical | Configure SSO & user roles | Tom Becker | 2026-08-17 | 2026-08-21 | 5 | 0% | Not Started
R-10 | Realize | Data | Execute vendor master migration to dev | Rina Takahashi | 2026-08-03 | 2026-09-04 | 33 | 0% | Not Started
R-11 | Realize | Testing | SIT cycle 1 | Maya Greenfield | 2026-09-07 | 2026-09-18 | 12 | 0% | Not Started
R-12 | Realize | Testing | SIT cycle 2 (defect fix retest) | Maya Greenfield | 2026-09-21 | 2026-10-02 | 12 | 0% | Not Started
R-13 | Realize | Change | Develop training materials & quick reference guides | Olivia Park | 2026-08-03 | 2026-09-04 | 33 | 0% | Not Started
D-01 | Deploy | Testing | UAT preparation & test script walkthrough | Maya Greenfield | 2026-10-05 | 2026-10-07 | 3 | 0% | Not Started
D-02 | Deploy | Testing | UAT execution | Karen Faulkner | 2026-10-08 | 2026-10-17 | 10 | 0% | Not Started
D-03 | Deploy | Testing | UAT sign-off | Daniel O'Connell | 2026-10-22 | 2026-10-23 | 2 | 0% | Not Started
D-04 | Deploy | Change | End-user training delivery (buyers, requesters, approvers) | Olivia Park | 2026-10-07 | 2026-10-16 | 10 | 0% | Not Started
D-05 | Deploy | Change | Supplier onboarding communications | Olivia Park | 2026-10-07 | 2026-10-16 | 10 | 0% | Not Started
D-06 | Deploy | Data | Production vendor master migration | Rina Takahashi | 2026-10-22 | 2026-10-28 | 7 | 0% | Not Started
D-07 | Deploy | Technical | Production cutover (config transport, integration switchover) | Yusuf Khalil | 2026-10-26 | 2026-10-29 | 4 | 0% | Not Started
D-08 | Deploy | PMO | Go-live readiness review | Sara Lindqvist | 2026-10-28 | 2026-10-29 | 2 | 0% | Not Started
D-09 | Deploy | PMO | Go-live | Sara Lindqvist | 2026-10-30 | 2026-10-30 | 1 | 0% | Not Started
N-01 | Run | Support | Hypercare ticket triage (Tier 1/2/3) | David Mensah | 2026-11-02 | 2026-11-27 | 26 | 0% | Not Started
N-02 | Run | Support | Daily hypercare standup | David Mensah | 2026-11-02 | 2026-11-27 | 26 | 0% | Not Started
N-03 | Run | Change | Adoption metrics tracking | Olivia Park | 2026-11-02 | 2026-11-27 | 26 | 0% | Not Started
N-04 | Run | PMO | Lessons learned workshop | Sara Lindqvist | 2026-11-23 | 2026-11-25 | 3 | 0% | Not Started
N-05 | Run | PMO | Transition to BAU support & project closure | Sara Lindqvist | 2026-11-25 | 2026-11-27 | 3 | 0% | Not Started

## Gantt
SAP Ariba SLP + Buying Implementation Plan - Acme Industrial
Task ID | Phase | Task | Start | End | W1 15-Jun | W2 22-Jun | W3 29-Jun | W4 06-Jul | W5 13-Jul | W6 20-Jul | W7 27-Jul | W8 03-Aug | W9 10-Aug | W10 17-Aug | W11 24-Aug | W12 31-Aug | W13 07-Sep | W14 14-Sep | W15 21-Sep | W16 28-Sep | W17 05-Oct | W18 12-Oct | W19 19-Oct | W20 26-Oct | W21 02-Nov | W22 09-Nov | W23 16-Nov | W24 23-Nov
P-01 | Prepare | Project kickoff meeting | 2026-06-15 | 2026-06-15
P-02 | Prepare | Governance model & steering committee setup | 2026-06-15 | 2026-06-19
P-03 | Prepare | Project charter sign-off | 2026-06-18 | 2026-06-22
P-04 | Prepare | Communication plan | 2026-06-22 | 2026-06-26
P-05 | Prepare | Ariba realm provisioning (test + prod) | 2026-06-15 | 2026-06-22
P-06 | Prepare | SAP integration prerequisites checklist | 2026-06-22 | 2026-06-26
P-07 | Prepare | Stakeholder map & change impact baseline | 2026-06-15 | 2026-06-26
E-01 | Explore | Supplier data discovery & cleansing strategy | 2026-06-29 | 2026-07-03
E-02 | Explore | Supplier registration form design workshop | 2026-07-06 | 2026-07-10
E-03 | Explore | Supplier qualification questionnaire design | 2026-07-07 | 2026-07-14
E-04 | Explore | Supplier segmentation & approval workflow design | 2026-07-13 | 2026-07-17
E-05 | Explore | Procurement policy review & catalog strategy | 2026-06-29 | 2026-07-03
E-06 | Explore | Guided Buying landing page & tile design | 2026-07-06 | 2026-07-10
E-07 | Explore | Approval rules & spend authorization matrix design | 2026-07-13 | 2026-07-17
E-08 | Explore | Catalog enablement plan (CIF, PunchOut, BMEcat) | 2026-07-20 | 2026-07-24
E-09 | Explore | Integration design (SLP master data, PR/PO, GR, invoice) | 2026-06-29 | 2026-07-17
E-10 | Explore | SSO & user provisioning design | 2026-07-14 | 2026-07-17
E-11 | Explore | Vendor master cleansing & migration approach | 2026-06-29 | 2026-07-24
E-12 | Explore | Training needs analysis | 2026-07-27 | 2026-07-31
R-01 | Realize | Configure registration & qualification forms | 2026-08-03 | 2026-08-14
R-02 | Realize | Configure supplier segmentation & approval flows | 2026-08-17 | 2026-08-21
R-03 | Realize | Configure supplier 360 view & modular questionnaires | 2026-08-24 | 2026-08-28
R-04 | Realize | Configure Guided Buying tiles, forms, and policies | 2026-08-03 | 2026-08-14
R-05 | Realize | Configure approval flows & substitute approvers | 2026-08-17 | 2026-08-21
R-06 | Realize | Configure commodity codes & catalog views | 2026-08-24 | 2026-08-28
R-07 | Realize | Onboard pilot catalogs (CIF + PunchOut) | 2026-08-31 | 2026-09-04
R-08 | Realize | Build SAP <-> Ariba integration (CIG / API) | 2026-08-03 | 2026-09-11
R-09 | Realize | Configure SSO & user roles | 2026-08-17 | 2026-08-21
R-10 | Realize | Execute vendor master migration to dev | 2026-08-03 | 2026-09-04
R-11 | Realize | SIT cycle 1 | 2026-09-07 | 2026-09-18
R-12 | Realize | SIT cycle 2 (defect fix retest) | 2026-09-21 | 2026-10-02
R-13 | Realize | Develop training materials & quick reference guides | 2026-08-03 | 2026-09-04
D-01 | Deploy | UAT preparation & test script walkthrough | 2026-10-05 | 2026-10-07
D-02 | Deploy | UAT execution | 2026-10-08 | 2026-10-17
D-03 | Deploy | UAT sign-off | 2026-10-22 | 2026-10-23
D-04 | Deploy | End-user training delivery (buyers, requesters, approvers) | 2026-10-07 | 2026-10-16
D-05 | Deploy | Supplier onboarding communications | 2026-10-07 | 2026-10-16
D-06 | Deploy | Production vendor master migration | 2026-10-22 | 2026-10-28
D-07 | Deploy | Production cutover (config transport, integration switchover) | 2026-10-26 | 2026-10-29
D-08 | Deploy | Go-live readiness review | 2026-10-28 | 2026-10-29
D-09 | Deploy | Go-live | 2026-10-30 | 2026-10-30
N-01 | Run | Hypercare ticket triage (Tier 1/2/3) | 2026-11-02 | 2026-11-27
N-02 | Run | Daily hypercare standup | 2026-11-02 | 2026-11-27
N-03 | Run | Adoption metrics tracking | 2026-11-02 | 2026-11-27
N-04 | Run | Lessons learned workshop | 2026-11-23 | 2026-11-25
N-05 | Run | Transition to BAU support & project closure | 2026-11-25 | 2026-11-27
Phase Legend: | Prepare | Explore | Realize | Deploy | Run

## RACI
SAP Ariba SLP + Buying Implementation Plan - Acme Industrial
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Workstream | Daniel O'Connell (Business Sponsor) | Sara Lindqvist (Program Manager) | Helena Ruiz (PMO Lead) | Anika Patel (SLP Lead) | James Whitaker (Buying Lead) | Yusuf Khalil (Integration Lead) | Rina Takahashi (Data Lead) | Tom Becker (Security Lead) | Maya Greenfield (Test Lead) | Olivia Park (Change Lead) | David Mensah (Support Lead) | Ravi Subramanian (Ariba Admin) | Karen Faulkner (UAT Lead)
Project governance | A | R | C | I | I | I | I | I | I | I | I | I | I
SLP - Registration & qualification | I | A | I | R | I | C | C | I | I | C | I | C | I
SLP - Supplier segmentation & workflows | I | A | I | R | I | C | I | I | I | I | I | C | I
Buying - Guided Buying & policies | I | A | I | I | R | C | I | I | I | C | I | C | I
Buying - Approvals & catalogs | I | A | I | I | R | C | I | I | I | I | I | C | I
Integration (SAP <-> Ariba) | I | A | I | C | C | R | C | C | I | I | I | C | I
Vendor master & data migration | I | A | I | C | C | C | R | I | I | I | I | I | I
Security, SSO, user provisioning | I | A | I | I | I | C | I | R | I | I | I | C | I
Testing (SIT) | I | A | I | C | C | C | I | I | R | I | I | I | I
UAT | A | C | I | C | C | I | I | I | C | C | I | I | R
Training & change management | I | A | I | C | C | I | I | I | I | R | I | I | I
Cutover & go-live | A | R | C | C | C | C | C | C | C | C | C | C | C
Hypercare | I | A | I | C | C | C | I | I | I | C | R | C | I

## RAID Log
SAP Ariba SLP + Buying Implementation Plan - Acme Industrial
ID | Type | Title | Description | Likelihood (H/M/L) | Impact (H/M/L) | Owner | Due Date | Status | Mitigation / Notes
R-01 | Risk | Vendor master data quality | Poor data quality in SAP delays SLP migration | H | H | Rina Takahashi | Explore phase | Open | Run profiling in Explore (AI-8); allocate cleansing sprints. Source: BRD Sec 5, Vendor Master Extract
R-02 | Risk | Supplier adoption of registration | Suppliers slow to complete self-registration; impacts SLP go-live | M | H | Olivia Park | Explore phase | Open | Supplier comms wave plan; concierge desk for top 50 suppliers
R-03 | Risk | CIG integration capacity | Cloud Integration Gateway throughput constraints during peak | M | M | Yusuf Khalil | Realize phase | Open | Performance test integration early; SAP support ticket on standby
R-04 | Risk | Catalog content readiness | Suppliers unable to deliver CIF/PunchOut catalogs on time | M | M | James Whitaker | Realize phase | Open | Stagger catalog onboarding; identify priority categories. Source: BRD Sec 2.3
R-05 | Risk | Approver hierarchy drift | SAP HR org changes invalidate approval matrix before go-live | L | H | James Whitaker | Deploy phase | Open | Lock org snapshot for cutover; daily sync pre-go-live
R-06 | Risk | CIG version compatibility with FPS01 | CIG version may not fully support S/4HANA 2023 FPS01 - to be re-verified before integration design lock | M | H | Yusuf Khalil | 2026-06-26 | Open | Source: Kickoff MoM item R-006, flagged by Yusuf Khalil. Follow-up via AI-2
R-07 | Risk | Training population size | 3,400 requesters across NA plants is large for 4-week Deploy window | M | M | Olivia Park | 2026-07-03 | Open | Source: Kickoff MoM, Olivia Park. Wave plan to be proposed by Week 3
R-08 | Risk | Duplicate vendor records | ~4 confirmed duplicate pairs in Vendor Master Extract (Grainger, Siemens, TCS, Apex Lab Reagents); 2 records missing tax IDs | H | M | Rina Takahashi | 2026-07-03 | Open | Source: Vendor Master Extract. Run dedup sprint in Explore. V-101455 (test record) flagged for deletion
A-01 | Assumption | Ariba realm provisioning SLA | SAP will provision Ariba test + prod realms within 5 business days of SOW signature |  |  | Ravi Subramanian | 2026-06-22 | Open | Source: Project Charter Sec 6; AI-1 (Marcus, due 22 Jun)
A-02 | Assumption | S/4HANA FPS01 on supported CIG release | SAP backend is on S/4HANA 2023 FPS01 and is supported by current CIG version |  |  | Yusuf Khalil | 2026-06-19 | Open | Source: Charter Sec 6; AI-2 (Tom + Ravi, due 19 Jun). Critical for integration design
A-03 | Assumption | Vendor master stays in S/4HANA | Vendor master remains system of record in S/4HANA; Ariba SLP is system of engagement |  |  | Rina Takahashi | 2026-07-03 | Open | Source: Charter Sec 6, confirmed in Kickoff MoM D-2
A-04 | Assumption | Single SSO IdP (Okta) | Single Okta instance is the IdP for all user populations; SCIM provisioning in scope |  |  | Tom Becker | 2026-06-26 | Open | Source: Charter Sec 6; BRD Sec 4; AI-9 (Tom + Yusuf, due 26 Jun)
A-05 | Assumption | Brazil NF-e fields not required in Phase 1 | Brazil tax registration NF-e fields are out of scope for Phase 1 SLP registration form |  |  | Hector Alvarez | 2026-07-03 | Open | Source: BRD O-1 (open item); AI-7 (Hector + Rina, due 3 Jul). If required, adds configuration effort
I-01 | Issue | (placeholder) | Open issue slot for team to populate |  |  |  |  | Open
I-02 | Issue | Capex committee approval matrix pending | Finance has not confirmed Capex committee members for approval matrix configuration |  |  | Felix Nguyen | 2026-07-03 | Open | Source: BRD O-2; AI-10 (Felix, due 3 Jul). Blocks Guided Buying approval rule config
I-03 | Issue | PunchOut go-live sequencing not confirmed | Priority order for PunchOut supplier go-live not agreed |  |  | James Whitaker | 2026-06-26 | Open | Source: BRD O-3. Decision D-3 (Kickoff MoM) confirmed Grainger, Staples, CDW, Dell as priority order
D-01 | Dependency | SAP basis team availability for CIG setup | SAP basis resources required for CIG configuration; blocks integration build |  |  | Yusuf Khalil | 2026-06-29 | Open | Confirm resource plan in Explore; align with AI-2
D-02 | Dependency | Procurement policy sign-off | Approved procurement policy required before Guided Buying design can be frozen |  |  | Daniel O'Connell | 2026-07-03 | Open | Source: BRD Sec 2.1
D-03 | Dependency | Master data governance decisions | Vendor master governance decisions required before migration scope can be locked |  |  | Rina Takahashi | 2026-07-03 | Open | Source: BRD Sec 5; MoM D-2
D-04 | Dependency | Top-8 CIF MRO supplier list | Lena Brandt to confirm top-8 MRO suppliers and contacts for CIF catalog loading |  |  | Lena Brandt | 2026-06-26 | Open | Source: Kickoff MoM AI-3. Blocks R-07 (onboard pilot catalogs)
D-05 | Dependency | Hypercare staffing model agreement | Bluewave/Acme split for hypercare L1/L2/L3 support must be agreed before Deploy phase |  |  | Sara Lindqvist | Realize phase | Open | Source: BRD O-4; MoM D-4 (Bluewave L2/L3 for 4 wks; Ravi team ramps L1)

## Milestones
SAP Ariba SLP + Buying Implementation Plan - Acme Industrial
Milestone | Target Date | Phase | Owner | Status
Project kickoff | 2026-06-15 | Prepare | Sara Lindqvist | Not Started
Design sign-off (SLP + Buying) | 2026-07-31 | Explore | Daniel O'Connell | Not Started
Integration build complete | 2026-09-11 | Realize | Yusuf Khalil | Not Started
SIT exit | 2026-10-02 | Realize | Maya Greenfield | Not Started
UAT sign-off | 2026-10-23 | Deploy | Daniel O'Connell | Not Started
GO-LIVE | 2026-10-30 | Deploy | Sara Lindqvist | Not Started
Hypercare exit / BAU transition | 2026-11-27 | Run | David Mensah | Not Started